## Slide 1: Airflow 3.3.2 migration roadmap
SENIOR MANAGEMENT UPDATE · OCTOBER 2026
Move the shared Airflow platform from 2.10.5 to 3.3.2 on Python 3.14 in two-week iterations. Every step is proven in a new QA environment first, then Dev and UAT, and every step can be rolled back.
Target go-live
Jan 16–18
2027, three-day weekend
Latest date
Feb 6–7
Jan 23–24 is the first fallback
Rollback
< 30 min
v2 stays untouched until retired
Buffer before go-live
17 days
Working days, Dec 21 – Jan 15
Dates assume a kickoff on Oct 12, 2026, US public holidays and the Dec 15–31 production freeze.
Notes: Key message: the target go-live is the three-day weekend of Jan 16-18, 2027 (Monday Jan 18 is a US holiday). If the go/no-go on Jan 13 fails, the fallback weekends are Jan 23-24 and Feb 6-7; Jan 30-31 is month-end and is avoided. Why this is realistic: the work runs in two-week iterations and UAT sign-off by all three teams is planned to finish on Dec 18, before the year-end freeze and holidays. The 17 working days between Dec 21 and Jan 15 are held as contingency for any testing that overruns, for leave and for final checks. The year-end freeze (Dec 15-31) means no production change in that window, so iteration 6 starts on Jan 4. Rollback: v2 and its database stay untouched and idle until retired, so rolling back means stopping v3 and restarting v2. The target is under 30 minutes, rehearsed in QA, Dev and UAT before production.

## Slide 2: Roadmap by iteration, October 2026 to January 2027
Workstream
Iter 1
Oct 12–23
Iter 2
Oct 26–Nov 6
Iter 3
Nov 9–20
Iter 4
Nov 23–Dec 4
Iter 5
Dec 7–18
Freeze
Dec 21–Jan 3
Iter 6
Jan 4–15
Iter 7
Jan 18–29
Gates
1
2
3
4
5
6
Readiness, Python 3.14
Scan, audit
Image, Helm
Teams fix DAGs on v2
Fix + release
QA environment (new)
QA build
QA tests
Dev (shared)
Infra
Cutover
UAT (shared)
Infra
Cutover
Sign-off by team
LnF
Capital, PnL
Production prep
Infra, plan
Final checks
Go-live, hypercare
Go-live Jan 16–18
Hypercare
Blue: platform team · Orange: DAG-owning teams · Navy: production · Grey band: freeze Dec 15–31 · Hatched: holidays · Dashed: float
1
Nov 6
QA sign-off
2
Nov 20
Dev stable
3
Dec 4
LnF sign-off
4
Dec 18
UAT sign-off
5
Jan 13
Go/no-go
6
Jan 16–18
Production go-live
Notes: Read top to bottom, left to right. Each column is a two-week iteration. The QA environment is new and is built in iteration 1, so the first migration run never touches the shared Dev environment. Iteration 2 builds the Airflow 3 image and Helm design and runs the QA migration and rollback tests. Dev is cut over in iteration 3 and UAT in iteration 4, each in a short announced window with a rollback test. LnF signs off its DAGs in iteration 4 and Capital and PnL in iteration 5. Production infrastructure and the runbook are ready before the Dec 15 freeze (infra only, no traffic). Dec 21-Jan 3 is deliberately empty: it is the year-end freeze and holidays, and it is the buffer for any testing that overruns. Iteration 6 is final checks with go/no-go on Jan 13 and the go-live weekend Jan 16-18. Hypercare runs from Jan 19 with Airflow 2 on standby.

## Slide 3: Iterations and exit gates
Iteration | Dates | Scope | Exit gate
Iter 1 | Oct 12–23 | DAG scan, Python 3.14 audit, vulnerability scan; QA build with a copy of the Dev DB | QA runs a copy of Dev on v2
Iter 2 | Oct 26–Nov 6 | v3 image, Helm design; QA DB migration (clone, trim, migrate, validate) and rollback test; Dev infrastructure | QA DB migrated and timed; QA signed off (latest Nov 11)
Iter 3 | Nov 9–20 | Dev DB migration, cutover and rollback test; UAT infrastructure | Dev stable; teams build on v3
Iter 4 | Nov 23–Dec 4 | UAT DB migration, cutover and rollback test; LnF full test and sign-off | LnF signed off
Iter 5 | Dec 7–18 | Capital and PnL full test and sign-off; production infrastructure, runbook; timed DB migration rehearsal on a production clone | UAT signed off; production ready; migration time known
Freeze | Dec 21–Jan 3 | Year-end freeze and holidays; overflow testing only | Held as buffer
Iter 6 | Jan 4–15 | Final checks, go/no-go Jan 13; production DB migration and go-live Jan 16–18 | Production on v3; v2 DB untouched
Iter 7 | Jan 18–29 | Hypercare; Airflow 2 on standby | No Sev1 for 7 days
Notes: Each iteration has one exit gate. Re-baselining happens at the end of every iteration, so the first review on Oct 23 confirms the Python 3.14 decision and the DAG scan results. Database migration: in every environment it is done on a clone of the Airflow 2 database, never on the original. The steps are: clone the v2 database (over a direct connection, not the connection pooler), trim old run history, run the Airflow 3.3.2 database migration, validate, and time it. The plan is a direct upgrade from 2.10.5 to 3.3.2; the QA migration in iteration 2 proves that, and only if it fails is an intermediate 2.11 step added, on the clone only. QA, Dev and UAT each repeat the same steps so the timing is known before production. Iteration 5 is where the production work happens before the Dec 15 freeze: production infrastructure and the timed migration rehearsal on a copy of the production database are planned for Dec 7-11, because new production changes stop on Dec 15. Whether infrastructure work and a read-only database clone are allowed during the freeze needs to be confirmed with change management. On go-live weekend the production database is cloned and migrated again, and the Airflow 2 database stays untouched, so rollback means stopping v3 and restarting v2. Production stays on Airflow 2 until the go-live weekend.

## Slide 4: Capacity and load by iteration
Planned load vs capacity, person-days (indicative)
Iter 1 · Oct 12–23
63 vs 56 · 113%
Iter 2 · Oct 26–Nov 6
79 vs 56 · 141%
Iter 3 · Nov 9–20
47 vs 56 · 84%
Iter 4 · Nov 23–Dec 4
31 vs 45 · 69%
Iter 5 · Dec 7–18
52 vs 56 · 93%
Iter 6 · Jan 4–15
22 vs 56 · 39%
Iter 7 · Jan 18–29
19 vs 50 · 38%
Grey: capacity · Blue: planned load · Orange: load above capacity
What it means
Iterations 1 and 2 need 113% and 141% of capacity.
Iterations 3 and 4 have room, at 84% and 69%.
Total demand reaches 101% of capacity on Dec 18, so there is no slack before year-end.
The buffer is about 45 days (17%) in Dec 21–Jan 15, shared with leave.
Levers: borrow BAU time in iterations 1–2, or let Dev infrastructure and the QA rollback test run into iteration 3.
5.6 FTE × working days · 8 days in Iter 4 (Nov 26–27 holidays) · leave assumed Dec 21–Jan 1
Notes: Capacity is 7 engineers at 80%, which is 5.6 FTE, times the working days in each iteration (10, or 8 in iteration 4 because of Nov 26-27). Leave of one week per person (about 28 person-days) is assumed to fall in Dec 21-Jan 1; leave taken earlier reduces the iteration it falls in. Load: the estimates for the five readiness items (7, 5, 3, 5 and 5 days) come from the team; the estimates for the other items are planning figures (QA environment 45, QA migration test 30, QA rollback 10, Dev infrastructure 12, Dev cutover 15 and rollback 8, UAT infrastructure 10, UAT cutover 12 and rollback 6, LnF sign-off support 10, Capital and PnL support 14, production infrastructure 15, runbook 10, prod-clone rehearsal 10, final checks 5, deployment 14, hypercare 16, DAG-fix support 15, dual-version CI 6, test plan 4, program management 3 per iteration) and should be replaced with the team estimates. Iteration 2 is the pinch: the image, Helm design, QA migration and rollback tests and Dev infrastructure all land in the same two weeks. Total planned demand through Dec 18 is 272 days against 268.8 of capacity (101%), so contingency sits in Dec 21-Jan 15: about 11 usable days in the year-end gap plus about 34 unused days in iteration 6, roughly 45 days or 17%.

## Slide 5: Key risks and how we handle them
Risk | How we handle it | Watch point
Python 3.14 is new; some libraries may not support it | Dependency audit and vulnerability scan finish in Iter 1; CI tests Python 3.11 and 3.14; fall back to 3.13 if a blocker remains | Decision Oct 23
QA build must finish in Iter 1, and Iters 1–2 are over capacity | Raise every infrastructure request before Oct 12; borrow BAU time; Dev infrastructure and the QA rollback test may run into Iter 3 | Requests in by Oct 9
Dev and UAT are shared; UAT sign-off is compressed | Cutover windows announced two weeks ahead; testers named by Nov 6; overflow uses the Dec 21–Jan 15 buffer | Testers named Nov 6
Production freeze Dec 15–31 | Production infrastructure and clone rehearsal done by Dec 11; confirm with change management that this work is allowed | Confirm by Oct 30
Production database migration runs long | Rehearse on a prod clone in Iter 5; size the window at 1.5× the measured time; trim history first | Rehearsal timing
Production go-live goes wrong | v2 and its database stay untouched; stop v3 and restart v2 in under 30 minutes; drilled in QA, Dev and UAT | UAT rollback drill
Notes: These are the six risks most likely to move the date. The first two are decided early: the Python 3.14 decision is due at the end of iteration 1 (Oct 23), and the QA environment has to be built in two weeks, which is only possible if every infrastructure request goes in before the Oct 12 kickoff. Iterations 1 and 2 are over capacity in the planning estimates (see the capacity slide); the mitigation is to borrow BAU time or let two items run into iteration 3, which has room. UAT sign-off by LnF has four working days after the Thanksgiving holidays, so testers need to be named early. The production freeze starts Dec 15, so production infrastructure and the clone rehearsal are planned for Dec 7-11. The last row is the main reassurance for production: Airflow 2 and its database are never modified.

## Slide 6: Decisions and assumptions
Decisions we need from management
1
Approve QA environment provisioning now, before the Oct 12 kickoff
2
Commit tester time from the three teams: Nov 30–Dec 4 (LnF) and Dec 7–18 (Capital, PnL)
3
Agree short Dev and UAT cutover windows in Iterations 3 and 4, announced two weeks ahead
4
Allow production infrastructure work and a clone rehearsal before the Dec 15 freeze
5
Reserve the Jan 16–18 change window, with Jan 23–24 and Feb 6–7 as fallbacks
Assumptions to confirm
Kickoff is Oct 12, 2026; a later start moves every date by the same amount
US public holidays; one week of leave per person, planned in Dec 21–Jan 1
The three teams release their own DAG fixes on v2 by Nov 6
Python 3.14 holds; otherwise 3.13 is the fallback
About 120 live DAGs; database size is measured in QA
No cutover at month-end or in the Dec 15–31 freeze
Re-baselined at every iteration review; first reviews Oct 23 (Python 3.14 decision) and Nov 6 (QA sign-off).
Notes: If management wants an earlier date, there is little room: sign-off by all three teams is already planned to finish on Dec 18, and the production freeze starts Dec 15. The only earlier option is the weekend of Jan 9-10, which would leave just three working days after the break for go/no-go and no overflow buffer; we do not recommend it. The assumptions on the right are the ones that would move the dates if they turn out wrong; the most sensitive are the start date, the QA environment being ready at the end of iteration 1, and the Python 3.14 check. Phase 2 (faster DAG storage and remote logging) is deliberately outside this roadmap.